## Sheet1
Waterfall Gantt Chart Template
Project Title: | Yosemite Digital Transformation |  | Start Date: |  | 2023-08-15
Project Manager: | Othman Saud AlRasheed |  | Estimated Completion Date: |  | 2023-12-19
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | ADD WEEKS AS NEEDED
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Phase/Milestone
Project Initiation | Me, Project Manager | 2023-08-15 | 2023-08-18 | 4 | bar: WEEK 1 M to WEEK 1 Tr
Scope Definition | Me, Project Manager | 2023-08-19 | 2023-08-23 | 5 | bar: WEEK 1 F to WEEK 2 Tr
Stakeholder Analysis | Me, Project Manager | 2023-08-24 | 2023-08-28 | 5 | bar: WEEK 2 F to WEEK 3 Tr
RACI Chart Creation | Me, Project Manager | 2023-08-29 | 2023-09-01 | 4 | bar: WEEK 3 F to WEEK 4 W
Vendor Management Setup | Moe, Vendor Manager | 2023-09-02 | 2023-09-06 | 5 | bar: WEEK 4 Tr to WEEK 5 W
Engineering Requirements and Design | Aliyah, Engineering Manager | 2023-09-07 | 2023-09-20 | 14 | bar: WEEK 5 Tr to WEEK 7 F
Build Storefront | Engineering Team | 2023-09-21 | 2023-10-04 | 14
Input Inventory Data | Vendor Managers | 2023-10-05 | 2023-10-10 | 6
Train Stefano’s on Platform | Vendor Managers | 2023-10-11 | 2023-10-17 | 7
Create Social Media Channels | Taylor, Marketing Manager | 2023-10-18 | 2023-10-24 | 7
Train Stefano’s on Social Media Use | Vendor Managers | 2023-10-25 | 2023-10-31 | 7
Build Recommendation Engine | Engineering Team | 2023-11-01 | 2023-11-21 | 15
Create Automated Sales Report | Vendor Managers | 2023-11-22 | 2023-11-28 | 7
Engage Stakeholders | Me, Project Manager | 2023-11-29 | 2023-12-05 | 7
Testing and Quality Assurance | Engineering Team | 2023-12-06 | 2023-12-12 | 7
Final Documentation and Closure | Me, Project Manager | 2023-12-13 | 2023-12-19 | 7
Add Phase/Milestone As Needed
[add tasks as needed]